## Sheet1
Epic | Story Title | User Story | Acceptance Criteria | Priority | Story Points
Epic 1: Resume Input & Parsing | Upload Resume | As a job seeker, I want to upload my resume (PDF/DOCX) so that the system can process my information. | Upload supports PDF/DOCX, validates file size & format. | High | 3
Epic 1: Resume Input & Parsing | Parse Resume | As a system, I want to parse skills, experience, and education so that I can match them to job postings. | spaCy extracts fields, JSON output validated. | High | 5
Epic 1: Resume Input & Parsing | Edit/Update Resume | As a job seeker, I want to edit/update my resume after upload so that I can refine my profile. | User can re-upload new file, system overwrites old one. | Medium | 3
Epic 2: Job Matching | Top 10 Job Matches | As a job seeker, I want to see the top 10 job matches so that I can quickly find relevant opportunities. | Results sorted by match score. | High | 5
Epic 2: Job Matching | API Integration | As a system, I want to query Canada Job Bank & Adzuna APIs so that I can recommend real, up-to-date jobs. | Successful API calls return JSON with job title, company, link. | High | 8
Epic 2: Job Matching | Match Score Display | As a job seeker, I want to see a match score for each job so that I know which roles fit me best. | SBERT score displayed on UI. | Medium | 3
Epic 3: Resume & Cover Letter Generation | Select Jobs | As a job seeker, I want to select up to 5 jobs so that I can generate tailored applications at once. | User can select checkboxes for jobs. | High | 5
Epic 3: Resume & Cover Letter Generation | Generate Resume | As a job seeker, I want the system to generate a customized resume per job so that I can highlight relevant skills. | Generated resume aligns with job description keywords. | High | 8
Epic 3: Resume & Cover Letter Generation | Generate Cover Letter | As a job seeker, I want the system to generate cover letters automatically so that I save time and effort. | Cover letter uses candidate + job details, editable by user. | High | 8
Epic 3: Resume & Cover Letter Generation | Download Documents | As a job seeker, I want to download resumes and cover letters in DOCX/PDF so that I can apply easily. | Export supports DOCX + PDF; filenames include job title. | High | 5
Epic 4: Enhancements | Missing Skills | As a job seeker, I want to see missing skills for jobs I apply to so that I can upskill accordingly. | Comparison highlights skills not in resume. | Medium | 5
Epic 4: Enhancements | ATS Scoring | As a job seeker, I want to simulate ATS scoring so that I can optimize my resume to pass filters. | ATS score (0–100%) displayed; suggestions shown. | High | 8
Epic 4: Enhancements | LinkedIn Consistency | As a job seeker, I want to check my LinkedIn profile consistency so that I present a unified professional image. | LinkedIn data vs. resume consistency check. | Low | 5
Epic 4: Enhancements | Dashboard | As a job seeker, I want a dashboard showing my applications and success rate so that I can track progress. | Dashboard displays job matches, applications, and outcomes. | Medium | 5
Epic 5: Output & Tracking | Batch Download | As a job seeker, I want to batch download all application documents so that I can apply to multiple jobs efficiently. | Zip file includes resumes + cover letters. | High | 5
Epic 5: Output & Tracking | Application Tracker | As a job seeker, I want an application tracker sheet (CSV/Excel) so that I can monitor my submissions. | Tracker includes job title, company, date applied, status. | Medium | 3
Epic 5: Output & Tracking | Redirect to Job Posting | As a job seeker, I want to be redirected to job posting pages so that I can apply immediately. | Each job result links to external job page. | High | 3